## CDP
Collaborative Development Package Component | Owner | Inc/Exc | Notes | Sprint 1 | Sprint 2 | Sprint 3
a) Screenshot of Git repository development activity | Joy | Include | Screenshot of GitHub w/Patch DG_53_903.kid files | IEMHV_Sprint 1 GitHub Screenshot.docx
b) Source Code, Test Frameworks, Application Programming Interface (API) Frameworks, Third party | James | Include | For this enhancement, source code will be in DG_53_903.kid files | DG_53_903_V1.KID
c) Dependencies including URLs | James | Exclude | The only Increase MHV dependency is a current VistA environment, which is basically owned and maintained by the VA. No relevant dependencies to include. | na | na | na
d) Tests, test scripts and test data | James | Include | Documents developer unit test results (via attachmate emulator capture tool) | IEMHV_UNIT_TEST_CAPTURE_V1.doc
e) Test configuration file | Bill | Exclude | The configuration for the ‘application’ is VistA itself. BC documented that configuration not necessary for this innovation. 10/1 | na | na | na
f) Installation Guide | James | Include | Standard instructions for vista patch installation | IEMHV_INSTALL_GUIDE_V1.doc
g) System Administration Guide | James | Exclude | This enhancement is not a standalone or distinct system requiring administration; there are no system administration functions/instructions to provide. | na | na | na
h) Technical Manual | James | Include | Standalone doc, notate as additional content for existing VistA Registration Technical Manual => Pre-registration content | IEMHV_TECHNICAL_MANUAL_V1.doc
i) Testing Manual | Bill | Include | Test scenarios w/screen shots | IEMHV_Testing_Manual_v1.1.docx
j) Developer Guide | James | Include | Necessary to guide a developer in open source community in setting up the environment to compile, test, etc… It is very important to OSHERA certification. | IEMHV_DEVELOPER_GUIDE_V1.doc
k) User Manual | Bill | Include | Standalone doc, notate as CHANGE PAGES for existing VistA Registration User Manual => Pre-registration content | IEMHV_dg_5_3_p858_reg_um Change Pages v.1.doc
l) Release Notes including a detailed description of changes since the previous release, bug fixes, known issues | James | Include | Content of patch description; leverage past release notes | IEMHV_RELEASE_NOTES_V1.doc
m) and a manifest of remaining items to complete the project | Joy | Include |  | IEMHV_PROJECT_MANIFEST_V1.doc

## Product Backlog
User Story ID | User Story Name | User Story Description | User Story Statement | Type | Acceptance Criteria | Sprint | Status
IEMVH_Vista_MHV_Alert | Add/Display VistA alert for MHV enrollment | Provide an alert within VistA under certain conditions, reminding the User to populate MHV enrollment fields. | As a VistA user, during pre-registration of a Patient, under certain conditions I want an alert to display to remind me to capture the Patient's MHV enrollment status. | User Feature | An alert is provided (on Patient VistA screen) to be utilized during Patient pre-registration which reminds the VistA user to discuss MHV with the Patient. | 1 | Done
IEMVH_Vista_MHV_Social_Question | Add/Display VistA MHV enrollment socialization question | Provide a field within VistA to capture whether or not the Patient has been socialized to enrolling in MyHealtheVet. | As a VistA user, during pre-registration of a Patient, I want to capture whether the Patient's Health Care provider has talked to them about enrolling in MHV and record any negative response to the question and the reason why. I want the information to be accessible the next time the Patient goes thru pre-registration. | User Feature | A field is provided (on Patient VistA screen) to be utilized during Patient pre-registration which enables the VistA user to record whether the Patient has been already been socialized to enrolling in MHV and the Patient's response. | 1 | Done
IEMVH_Vista_MHV_Enroll_Three_Questions | Add/Display VistA MHV Enrollment questions (3) | Provide fields within VistA to capture the Patient's responses for three MHV enrollment questions. | As a VistA user, during pre-registration of a Patient, I want to capture the Patient's responses for three MHV enrollment questions and make the responses accessible the next time the Patient goes thru the pre-registration process. | User Feature | Three questions are displayed (on MHV VistA screen) on the Patient pre-registration screen which enables the VistA user to enter the patient responses to each question. | 2 | In Progress
IEMVH_Mod_DCC | Add MHV Data Consistency Check | Add MHV related fields to the Vista Data Consistency Check module | Modify Data Consistency Check to ensure newly added MHV related fields are populated as desired. | Validation Check |  | 3 | Not Started

## Sprint1
Sprint Story: Provide an alert within VistA under certain conditions, reminding the User to populate MHV enrollment fields. Story Point: |  |  |  | Sprint Start/End = 9/08/2014 – 10/3/2014 | Sprint 1 Max Capacity | Estimated Work Hrs
Task Name | Hours Est | Hours Rem | Owner | Sprint Duration = 20 days | James = 140 hrs | 160
ANA: Create first draft of Alert user story | 0.5 | 0 | Kristen K | Max Sprint Capacity = 7hrs x 20 = 140 hrs | Bill = 140 x .25 = 35 hrs | 33
ANA: Schedule first working session | 0.5 | 0 | Kristen K |  | Kristen = 140 x .50 = 70 hrs | 4
ANA: Facilitate first working session | 1 | 0 | Kristen K |  | Joy = 35 hrs
ANA: Update user story after working sessions | 2 | 0 | Kristen K
ANA: Communications; emails, etc | 2 | 0 | Kristen K
6
Test: Create Test Plan | 3 |  | B. Frey
Test: Create Sprint Story Test Scripts | 2 |  | B. Frey
Test: Execute Sprint Story Tests | 8 |  | B. Frey
Test: Retest any code fixes required | 2 |  | B. Frey
Test: Update Test Plan with test results | 1 |  | B. Frey
Test: Prepare for Demo and Perform Demo at Sprint Review | 2 |  | B. Frey
18
DEV: Research existing VistA Alert Algorithms | 24 | 0 | JH
DEV: Design MHV Vista Alert | 8 | 0 | JH
DEV: Code MHVVistA Alert Enhancement | 16 | 0 | JH
DEV: Unit Test MHVVistA Alert Enhancement | 8 | 0 | JH
56
Sprint Story: Provide a field within VistA to capture whether or not the Patient has been socialized to enrolling in MyHealtheVet. Story Point:
Task Name | Hours Est | Hours Rem | Owner
ANA: Create first draft of user story | 1.5 | 0 | Kristen K
ANA: Schedule second working session | 0.5 | 0 | Kristen K
ANA: Facilitate second working session | 1 | 0 | Kristen K
ANA: Update user stories after working sessions | 6 | 0 | Kristen K
ANA: Communications; emails, etc | 2 | 0 | Kristen K
11
Test: Create Sprint Story Test Scripts | 2 |  | B. Frey
Test: Execute Sprint Story Tests | 8 |  | B. Frey
Test: Retest any code fixes required | 2 |  | B. Frey
Test: Update Test Plan with test results | 1 |  | B. Frey
Test: Prepare for Demo and Perform Demo at Sprint Review | 2 |  | B. Frey
15
DEV: Design 'Socialization' enhancement | 40 | 0 | JH
DEV: Code 'Socialization' enhancement | 32 | 0 | JH
DEV: Unit Test 'Socialization' enhancement | 32 | 0 | JH
104

## Sprint 2
Sprint Story: Provide fields within VistA to capture the Patient's responses for three MHV enrollment questions. |  |  |  | Sprint Start/End = 10/06/2014 – 10/31/2014 | Sprint 1 Max Capacity | Estimated Work Hrs
Task Name | Hours Est | Hours Rem | Owner | Sprint Duration = 19 days | James = 90 hrs | 90
SQA: Create Sprint Story Test Scripts | 2 |  | B. Frey | Max Sprint Capacity = 8hrs x 19 = 152 hrs | Bill = 152 x .25 = 38 hrs | 34
SQA: Execute Sprint Story Tests | 8 |  | B. Frey
SQA: Retest any code fixes required | 2 |  | B. Frey
SQA: Update Test Manual with test scripts for CDP | 2 |  | B. Frey
SQA: Prepare for Demo and Perform Demos during sprint | 2 |  | B. Frey
16
DEV: Technical Research | 24 |  | JH
DEV: Design MHV enrollment field enhancement | 24 |  | JH
DEV: Code MHV enrollment field enhancement | 24 |  | JH
DEV: Unit Test MHV enrollment field enhancement | 16 |  | JH
DEV: Update technical documents for CDP | 2 |  | JH
90
ANA: Update user story and create final draft | 8 |  | B. Frey
ANA: Facilitate working sessions & SME collaborations | 8 |  | B. Frey
ANA: Update User Manual for CDP | 2 |  | B. Frey
18

## Sprint 3
Sprint Story: Add MHV related fields to the Vista Data Consistency Check module. Story Point:
Task Name | Hours Est | Hours Rem | Owner

## PCMMR
Month | Holidays | Deployable Days | Sites Installed
November | Thanksgiving week | 6 | 12
December | Christmas week & New Years Eve | 14 | 28
January | n/a | 17 | 34
February | n/a | 16 | 32
March | n/a | 16 | 32
138