## CDP
Collaborative Development Package Component | Owner | Notes
a) Screenshot of Git repository development activity | James | Include
b) Source Code, Test Frameworks, Application Programming Interface (API) Frameworks, Third party | James | Include
c) Dependencies including URLs | James | Exclude; the only Increase MHV dependency is a current VistA environment, which is basically owned and maintained by the VA. Nothing to provide here.
d) Tests, test scripts and test data | Bill | Exclude; the Testing Manual will contain the test scripts
e) Test configuration file | Bill | Exclude; for an innovation package this probably has minimal value. We could include the config info in the testing manual.
f) Installation Guide | James | Include
g) System Administration Guide | James | Exclude; this enhancement is not a standalone or distinct system requiring administration, there are no system administration functions/instructions to provide.
h) Technical Manual | James | Include
i) Testing Manual | Bill | Include
j) Developer Guide | James | Exclude; this enhancement is not intended to be a development tool or an environment hosting new development, so there will be no developer guide.
k) User Manual | Bill | Modify; a formal user manual for a short innovation project is overkill but a brief user guide to the MHV enrollment enhancement would be useful.
l) Release Notes including a detailed description of changes since the previous release, bug fixes, known issues | James | Include
m) and a manifest of remaining items to complete the project | Joy | Include

## Product Backlog
User Story ID | User Story Name | User Story Description | User Story Statement | Type | Acceptance Criteria | Sprint
IEMVH_Vista_MHV_Alert | Add/Display VistA alert for MHV enrollment | Provide an alert within VistA under certain conditions, reminding the User to populate MHV enrollment fields. | As a VistA user, during pre-registration of a Patient, under certain conditions I want an alert to display to remind me to capture the Patient's MHV enrollment status. | User Feature | An alert is provided (on Patient VistA screen) to be utilized during Patient pre-registration which reminds the VistA user to discuss MHV with the Patient. | 1
IEMVH_Vista_MHV_Enroll_Discussion | Add/Display VistA MHV enrollment discussion field | Provide a field within VistA to capture whether or not the Patient has been socialized to enrolling in MyHealtheVet. | As a VistA user, during pre-registration of a Patient, I want to capture whether the Patient's Health Care provider has talked to them about enrolling in MHV and record any negative response to the question and the reason why. I want the information to be accessible the next time the Patient goes thru pre-registration. | User Feature | A field is provided (on Patient VistA screen) to be utilized during Patient pre-registration which enables the VistA user to record whether the Patient has been already been socialized to enrolling in MHV and the Patient's response. | 1
IEMVH_Vista_MHV_Enroll_Three_Questions | Add/Display VistA MHV Enrollment questions (3) | Provide fields within VistA to capture the Patient's responses for three MHV enrollment questions. | As a VistA user, during pre-registration of a Patient, I want to capture the Patient's responses for three MHV enrollment questions and make the responses accessible the next time the Patient goes thru the pre-registration process. | User Feature | Three questions are displayed (on MHV VistA screen) on the Patient pre-registration screen which enables the VistA user to enter the patient responses to each question. | 2
IEMVH_Mod_DCC | Add MHV Data Consistency Check | Add MHV related fields to the Vista Data Consistency Check module | Modify Data Consistency Check to ensure newly added MHV related fields are populated as desired. | Validation Check |  | 3

## Sprint1
Sprint Story: Provide an alert within VistA under certain conditions, reminding the User to populate MHV enrollment fields. Story Point: |  |  |  | Sprint Start/End = 9/08/2014 – 10/3/2014 | Sprint 1 Max Capacity
Task Name | Hours Est | Hours Rem | Owner | Sprint Duration = 20 days | James = 140 hrs
ANA: Create first draft of Alert user story | 0.5 | 0 | Kristen K | Max Sprint Capacity = 7hrs x 20 = 140 hrs | Bill = 140 x .25 = 35 hrs
ANA: Schedule first working session | 0.5 | 0 | Kristen K |  | Kristen = 140 x .50 = 70 hrs
ANA: Facilitate first working session | 1 | 0 | Kristen K |  | Joy = 35 hrs
ANA: Update user story after working sessions | 2 | 1 | Kristen K
ANA: Communications; emails, etc | 2 | 1 | Kristen K
6
Test: Create Test Plan | 3 |  | B. Frey
Test: Create Sprint Story Test Scripts | 2 |  | B. Frey
Test: Execute Sprint Story Tests | 8 |  | B. Frey
Test: Retest any code fixes required | 2 |  | B. Frey
Test: Update Test Plan with test results | 1 |  | B. Frey
Test: Prepare for Demo and Perform Demo at Sprint Review | 2 |  | B. Frey
18
DEV: Research existing VistA Alert Algorithms | 24 | 8 | JH
DEV: Design MHV Vista Alert | 8 | 4 | JH
DEV: Code MHVVistA Alert Enhancement | 16 | 16 | JH
DEV: Unit Test MHVVistA Alert Enhancement | 8 | 8 | JH
56
Sprint Story: Provide a field within VistA to capture whether or not the Patient has been socialized to enrolling in MyHealtheVet. Story Point:
Task Name | Hours Est | Hours Rem | Owner
ANA: Create first draft of user story | 1.5 | 0 | Kristen K
ANA: Schedule second working session | 0.5 | 0 | Kristen K
ANA: Facilitate second working session | 1 | 0 | Kristen K
ANA: Update user stories after working sessions | 6 | 2 | Kristen K
ANA: Communications; emails, etc | 2 | 1 | Kristen K
11
Test: Create Sprint Story Test Scripts | 2 |  | B. Frey
Test: Execute Sprint Story Tests | 8 |  | B. Frey
Test: Retest any code fixes required | 2 |  | B. Frey
Test: Update Test Plan with test results | 1 |  | B. Frey
Test: Prepare for Demo and Perform Demo at Sprint Review | 2 |  | B. Frey
15
DEV: Design 'Socialization' enhancement | 40 | 40 | JH
DEV: Code 'Socialization' enhancement | 32 | 32 | JH
DEV: Unit Test 'Socialization' enhancement | 32 | 32 | JH
104

## Sprint 2
Sprint Story: Provide fields within VistA to capture the Patient's responses for three MHV enrollment questions. Story Point:
Task Name | Hours Est | Hours Rem | Owner

## Sprint 3
Sprint Story: Add MHV related fields to the Vista Data Consistency Check module. Story Point:
Task Name | Hours Est | Hours Rem | Owner